## Sheet1
Sprint Retrospective
| What went well | What went poorly | What ideas do you have | How should we take action
| This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
| Example : All tasks were completed on time. Team communication was seamless. | Requirements changed mid-sprint. | Plan for a buffer to handle scope changes. | Set stricter deadlines for finalizing requirements. | Example
1 | Successfully designed and implemented a Retrieval-Augmented Generation (RAG) architecture tailored for SAP advisory use cases. | Faced difficulties in accurately parsing complex PDF documents, especially those containing tables and structured academic data. | Enhance the conversational agent to provide more natural, context-aware, and human-like interactions for students. | Optimize the RAG pipeline by improving indexing strategies and reducing retrieval time for faster responses.
2 | Built a functional document ingestion pipeline that allows administrators to upload brochures and SAP-related documents. | Encountered challenges while designing and optimizing the RAG pipeline for efficient retrieval and response generation. | Introduce a voice-enabled interface to allow users to interact with the chatbot using speech for better accessibility. | Adopt advanced document parsing tools to ensure accurate extraction of structured and tabular data from PDFs.
3 | Achieved dynamic knowledge base updating, enabling the chatbot to reflect newly uploaded information without retraining. | Observed latency issues during query processing, particularly when handling large document datasets. | Implement multilingual support to assist international students in their native languages more effectively. | Strengthen the validation layer (e.g., Self-RAG) to minimize hallucinations and ensure factual correctness.
4 | Clearly defined user roles including students, educators, and administrators for structured system interaction. | Ensuring zero hallucination responses proved difficult due to limitations of LLM behavior. | Improve document parsing techniques to accurately extract structured data such as fee tables and credit systems. | Improve integration between the conversational agent and backend systems to ensure smoother interaction flow.
5 | Identified and addressed a real-world problem where students lack clarity about SAP streams, credits, and semesters. | Integration between the conversational agent and the RAG backend was not fully stable or seamless. | Add personalized recommendations based on student preferences, academic background, and target universities. | Conduct real-world testing with students to identify usability issues and refine chatbot responses.
6 | Established a scalable backend approach that supports future enhancements like GraphRAG and conversational agents. | Initial setup of vector databases and embeddings required significant experimentation and debugging. | Integrate GraphRAG to enable multi-hop reasoning across related concepts like universities, visas, and SAP modules. | Implement caching and efficient query routing to reduce latency and improve system performance.
| Developed a foundational conversational flow that allows users to interact naturally with the chatbot interface. | Handling multilingual queries and maintaining consistency in responses was more complex than expected. | Develop a feedback mechanism where users can rate responses to continuously improve system accuracy. | Gradually transition to scalable cloud infrastructure to support global usage and higher user loads.